## Worksheet
Id | Code | Tasks | Project | Assigned | Due Date | Hours Logged | Task
11249 | APS-G-10875 | In front end , If the customer's rewards & Coupons are applied, store the rewards amount in the order table(Need to check both COD & RMS) | APS Garland | Sangeetha M | Tue 28 Nov 2023 | 8 hrs 46 mins | In Progress
11220 | 00-10846 | Weekly KT session | Santhila's Internal Work | Sangeetha M,Vigneshwaran A,Prabakaran V | Sat 25 Nov 2023 | 0 hrs 10 mins | In Progress
11158 | APS-G-10784 | Testing and bug fixing and do modifications in code as per requirement | APS Garland | Sangeetha M | Mon 20 Nov 2023 | 38 hrs | In Progress
11141 | APS-G-10767 | In the admin panel, 'Recurring Orders' - the 'Unsubscribe' a selective recurring order option is not working | APS Garland | Sangeetha M | Fri 17 Nov 2023 | 7 hrs 35 mins | In Progress
11137 | APS-G-10763 | Test Recurring Order, Manual Order, Reward points after merge | APS Garland | Sangeetha M | Fri 17 Nov 2023 | 1 hrs 5 mins | Completed
11069 | WHB-10764 | Women's Hostel Bangalore - Analysis and planning | Womens Hostel in Bangalore | Brindha Devi V,Ranjith Prabhakaran P,Sangeetha M | Tue 14 Nov 2023 | 94 hrs 48 mins | In Progress
11068 | APS-G-10696 | Study about Express JS for API creation | APS Garland | Sangeetha M,Vigneshwaran A,Prabakaran V | Sat 11 Nov 2023 | 49 hrs 42 mins | Completed
11046 | LMS-10726 | LMS APIs For MileStone II | LMS | Giri Shankar,Prabakaran V,Sangeetha M,Vigneshwaran A | Mon 20 Nov 2023 | 41 hrs 33 mins | In Progress
11037 | MYRUN-10665 | 10 - Advance search in today's deals, latest products - API Creation | Myrunciit | Sangeetha M | Wed 08 Nov 2023 | 17 hrs 12 mins | Completed
10979 | MYRUN-10662 | R&D for 17 WS[WEB SERVICES] FOR MYRUNCIT | Myrunciit | Giri Shankar,Indumathi,Prabakaran V,Sangeetha M,Sabarieswaran V R | Thu 02 Nov 2023 | 83 hrs 49 mins | Completed
10969 | APS-G-10597 | Update Total when select Flat rate shipping method | APS Garland | Sangeetha M | Wed 01 Nov 2023 | 12 hrs 30 mins | Completed
10945 | APS-G-10573 | The recurring Sub Total Should be displayed in the Indivudual Order ,Print ,Order Summary ,My account | APS Garland | Sangeetha M | Mon 30 Oct 2023 | 1 hrs 22 mins | Completed
10944 | APS-G-10572 | In Admin , List the order status with Recurring order details | APS Garland | Sangeetha M | Mon 30 Oct 2023 | 6 hrs 30 mins | Completed
10943 | APS-G-10571 | In Admin , Indivudual Order - If the order have a recurring order, add a 'View Recurring Details' option | APS Garland | Sangeetha M | Mon 30 Oct 2023 | 1 hrs 20 mins | Completed
10942 | APS-G-10570 | In Admin , Individual Order - If the order have recurring order , Disable order status | APS Garland | Sangeetha M | Mon 30 Oct 2023 | 2 hrs 40 mins | Completed
10928 | APS-G-10556 | KT Session | APS Garland | Indumathi,Sangeetha M,Mohamed Ashik,Vigneshwaran A,Prabakaran V,Logeswari Ramesh | Sat 28 Oct 2023 | 15 hrs 20 mins | Completed
10920 | APS-G-10548 | Recurring Order - In Admin, Modify the workflow | APS Garland | Sangeetha M | Fri 27 Oct 2023 | 7 hrs 46 mins | Completed
10919 | APS-G-10547 | Recurring Order - In Front End , store the recurring details in the recurring table | APS Garland | Sangeetha M | Thu 26 Oct 2023 | 10 hrs 48 mins | Completed
10912 | APS-G-10540 | Testing demo server | APS Garland | Indumathi,Sangeetha M,Mohamed Ashik,Vigneshwaran A,Prabakaran V | Thu 26 Oct 2023 | 6 hrs 57 mins | Completed
10854 | APS-G-10482 | Testing - Banner and images in demo server/local test server | APS Garland | Sangeetha M | Tue 17 Oct 2023 | 4 hrs 49 mins | Completed
10834 | APS-G-10464 | Front End- Update the product sub total amount based on selected order dates + Coupon applied + Shipping added | APS Garland | Sangeetha M | Mon 16 Oct 2023 | 48 hrs 23 mins | Completed
10720 | APS-G-10350 | Week end KT Session | APS Garland | Praveen S,Sangeetha M,Vigneshwaran A,Prabakaran V,Indumathi | Sat 07 Oct 2023 | 4 hrs 36 mins | Completed
10705 | APS-G-10463 | Front End- Update the product sub total amount based on selected order dates | APS Garland | Sangeetha M | Fri 06 Oct 2023 | 28 hrs 29 mins | In Progress
10704 | APS-G-10463 | Front End - Show Recurring Order details | APS Garland | Sangeetha M | Thu 05 Oct 2023 | 22 hrs 52 mins | In Progress
10655 | APS-G-10293 | Manipulation of Datatable to Show/Edit page for Recurring Sub Order | APS Garland | Sangeetha M | Tue 03 Oct 2023 | 18 hrs 7 mins | In Progress
10638 | APS-G-10268 | Demo server Testing - After Deployement | APS Garland | Indumathi,Sangeetha M,Vigneshwaran A,Prabakaran V | Sat 30 Sep 2023 | 7 hrs 48 mins | Completed
10548 | APS-G-10178 | Test Setting Module after some git Merges | APS Garland | Sangeetha M | Sat 23 Sep 2023 | 2 hrs 6 mins | In Progress
10546 | APS-G-10262 | Weekly KT session | APS Garland | Prabakaran V,Indumathi,Sangeetha M,Vigneshwaran A,Logeswari Ramesh | Sat 23 Sep 2023 | 3 hrs 38 mins | Completed
10489 | APS-G-10119 | Recurring Order - Admin Panel - Edit Page | APS Garland | Sangeetha M | Fri 15 Sep 2023 | 38 hrs 51 mins | In Progress
10488 | APS-G-10118 | Recurring Order - Admin Panel - Index Page | APS Garland | Sangeetha M | Fri 15 Sep 2023 | 27 hrs 49 mins | In Progress
10487 | APS-G-10117 | Recurring Order - Admin Panel - Add this as Sub menu of Sales | APS Garland | Sangeetha M | Fri 15 Sep 2023 | 8 hrs 10 mins | In Progress
10480 | APS-G-10110 | Team Discussion about Recurring Order module and implementation | APS Garland | Sangeetha M,Prabakaran V | Fri 15 Sep 2023 | 0 hrs 15 mins | Completed
10466 | APS-G-10096 | Validating Recurring Order Subscription Form while submitting | APS Garland | Sangeetha M | Thu 14 Sep 2023 | 8 hrs 39 mins | In Progress
10403 | APS-G-10033 | Testing Social Login in demo server (https://apsgarlands.santhila.com/public/login) | APS Garland | Navin E,Indumathi,Sangeetha M,Mohamed Ashik,Vigneshwaran A,Prabakaran V,Logeswari Ramesh,Praveen S | Sat 09 Sep 2023 | 50 hrs 20 mins | Completed
10348 | APS-G-9979 | Recurring Order - Storefront - Craete Validation | APS Garland | Sangeetha M | Wed 06 Sep 2023 | 30 hrs 17 mins | In Progress
10311 | APS-G-9942 | Create Admin Panel - Enable/Disable Setting for Testimonial | APS Garland | Sangeetha M | Tue 05 Sep 2023 | 3 hrs 55 mins | In Progress
10263 | APS-G-9894 | Social Login - Create A Demo API for social login with gmail and Facebook | APS Garland | Sangeetha M | Sat 02 Sep 2023 | 1 hrs 12 mins | In Progress
10251 | APS-G-9882 | Modify Testimonial slider Card | APS Garland | Sangeetha M | Fri 01 Sep 2023 | 3 hrs 15 mins | In Progress
10248 | APS-G-9901 | Recurring Order - Integrate Store Front partial view file in Order Check out page | APS Garland | Sangeetha M | Fri 01 Sep 2023 | 19 hrs 23 mins | In Progress
10247 | APS-G-9901 | Recurring Order - Create Store Front partial view file | APS Garland | Sangeetha M | Fri 01 Sep 2023 | 15 hrs 8 mins | In Progress
10246 | APS-G-9901 | Recurring Order - Craete Admin panel Setting option | APS Garland | Vigneshwaran A,Sangeetha M | Fri 01 Sep 2023 | 14 hrs 38 mins | In Progress
10226 | APS-G-10351 | Daily Stand Up Meeting[Morning / Evening Session] | APS Garland | Navin E,Indumathi,Sangeetha M,Mohamed Ashik,Prabakaran V,Logeswari Ramesh,Giri Shankar | -- | 1 hrs 42 mins | Completed
10225 | APS-G-10080 | Daily Stand Up Meeting[Morning Session] | APS Garland | Navin E,Indumathi,Sangeetha M,Mohamed Ashik,Prabakaran V,Logeswari Ramesh,Giri Shankar | -- | 8 hrs 48 mins | Completed
10209 | APS-G-9840 | Clone the latest code from Git and Integrate the Testimonial Module with it | APS Garland | Sangeetha M | Thu 31 Aug 2023 | 12 hrs 14 mins | In Progress
10174 | APS-G-9805 | Test Application for Client Demo | APS Garland | Indumathi,Sangeetha M,Prabakaran V | Tue 29 Aug 2023 | 7 hrs 54 mins | Completed
10173 | APS-G-9804 | Testimonial - Make Crud Functionality | APS Garland | Sangeetha M | Tue 29 Aug 2023 | 6 hrs 24 mins | In Progress
10172 | APS-G-9803 | Testimonial - Modify the Menu Files to Testimonial for admin panel (Initial Setup) | APS Garland | Sangeetha M | Tue 29 Aug 2023 | 4 hrs 19 mins | In Progress
10144 | APS-G-9775 | Correction & Bug Fixing task based on Discussed points in Team Demo Session | APS Garland | Sangeetha M | Sat 26 Aug 2023 | 5 hrs 52 mins | Not Started
10136 | APS-G-9767 | Create a page for Terms & Conditions | APS Garland | Sangeetha M | Fri 25 Aug 2023 | 3 hrs 20 mins | In Progress
10119 | APS-G-9758 | Analyse all Reports with filters (Just Analyse no need to chnage code) | APS Garland | Sangeetha M,Mohamed Ashik | Thu 24 Aug 2023 | 2 hrs | In Progress
10109 | APS-G-9740 | RNG APS-G In admin Login Page , Need to change Caps in shop name | APS Garland | Sangeetha M | -- | 0 hrs 20 mins | Completed
10108 | APS-G-9739 | RND APS-G :Remove Tax Report | APS Garland | Sangeetha M | -- | 0 hrs 57 mins | Completed
10107 | APS-G-9738 | RND APS-G :In Reports , Need to check all filter | APS Garland | Sangeetha M | -- | 2 hrs 28 mins | Completed
10106 | APS-G-9737 | RND APS-G :Need to Check Latest Orders Count | APS Garland | Sangeetha M | -- | 2 hrs 28 mins | Completed
10105 | APS-G-9736 | RND APS-G :Need to Check Latest Reviews Count | APS Garland | Sangeetha M | -- | 1 hrs | Completed
10104 | APS-G-9735 | RND APS-G : Need to enable Keyword search option | APS Garland | Sangeetha M | -- | 0 hrs 29 mins | Completed
10103 | APS-G-9734 | RND APS-G :Need to Check Sales Analystic in in Dashboard page | APS Garland | Sangeetha M | -- | 0 hrs 36 mins | Completed
10087 | APS-G-9718 | Create Index page for Testimonials in Admin(Backend) | APS Garland | Sangeetha M | Tue 22 Aug 2023 | 7 hrs 35 mins | In Progress
10062 | APS-G-9693 | Create Slider for Testimonials in Store(Frontend) | APS Garland | Sangeetha M | Tue 22 Aug 2023 | 10 hrs 35 mins | In Progress
10043 | APS-G-9674 | Testimonial - Create a field in Setting table and store and retrieve the data to control over the visibility at Customer End | APS Garland | Sangeetha M | Mon 21 Aug 2023 | 6 hrs 39 mins | In Progress
9998 | APS-G-9673 | Update Testimonial Settings Admin Form | APS Garland | Sangeetha M | Fri 18 Aug 2023 | 7 hrs 3 mins | In Progress
9997 | APS-G-9628 | Store and Retrive stored Data in Admin Panel Testimonial Form Data from Database | APS Garland | Sangeetha M | Sat 19 Aug 2023 | 6 hrs 53 mins | In Progress
9996 | APS-G-9629 | Create Testimonial Settings Admin From | APS Garland | Sangeetha M | Fri 18 Aug 2023 | 4 hrs 6 mins | In Progress
9983 | APS-G-9616 | Create Vision & Mission page | APS Garland | Sangeetha M | Thu 17 Aug 2023 | 0 hrs 34 mins | In Progress
9982 | APS-G-9615 | Create About Us page | APS Garland | Sangeetha M | Thu 17 Aug 2023 | 1 hrs 50 mins | In Progress
9978 | APS-G-9622 | Team discussion | APS Garland | Prabakaran V,Navin E,Indumathi,Sangeetha M,Mohamed Ashik,Logeswari Ramesh | Thu 17 Aug 2023 | 1 hrs 53 mins | Completed
9955 | APS-G-9626 | Create Testimonial Sidebar | APS Garland | Sangeetha M | Wed 16 Aug 2023 | 5 hrs 42 mins | In Progress
9953 | APS-G-9586 | Analyse Testimonial Flow | APS Garland | Sangeetha M | Wed 16 Aug 2023 | 3 hrs 50 mins | In Progress
9885 | APS-G-9518 | APS-G New product implements and code analyzing | APS Garland | Navin E,Indumathi,Sangeetha M,Mohamed Ashik,Vigneshwaran A,Prabakaran V | Fri 11 Aug 2023 | 175 hrs 38 mins | Completed
9861 | APS-G-9495 | APS-G need to display multiple Add-On products in the popup | APS Garland | Sangeetha M | Thu 10 Aug 2023 | 3 hrs 5 mins | Completed
9860 | APS-G-9494 | APS-G The image is not visible in the Add-On Products popup | APS Garland | Sangeetha M | Wed 09 Aug 2023 | 7 hrs 12 mins | Completed
9840 | APS-G-9474 | KT Session for APS Garlands | APS Garland | Navin E,Sangeetha M,Mohamed Ashik,Vigneshwaran A,Prabakaran V | Mon 07 Aug 2023 | 1 hrs 38 mins | Completed
9812 | APS-G-9446 | APS-G In home page , pop up functionality not working. | APS Garland | Sangeetha M | Sat 12 Aug 2023 | 1 hrs 56 mins | Completed
9811 | APS-G-9445 | APS-G RE-correct the calculation for function in add-on | APS Garland | Sangeetha M | Sat 12 Aug 2023 | 2 hrs 8 mins | Completed
9810 | APS-G-9444 | APS-G And make it to that product into add-cart | APS Garland | Sangeetha M | Sat 12 Aug 2023 | 4 hrs 3 mins | Completed
9809 | APS-G-9443 | APS-G show the add-on products in the popup. | APS Garland | Sangeetha M | Mon 07 Aug 2023 | 4 hrs 9 mins | Completed
9808 | APS-G-9442 | APS-G Add-On set popup on add-cart. | APS Garland | Sangeetha M | Sat 05 Aug 2023 | 2 hrs 38 mins | Completed
9787 | APS-G-9425 | APS-G UI Add Cart changes | APS Garland | Sangeetha M | Fri 04 Aug 2023 | 5 hrs 44 mins | Completed
9765 | APS-G-9403 | APS-G To verify that reviews are only allowed after purchasing the product | APS Garland | Sangeetha M | Fri 04 Aug 2023 | 3 hrs 39 mins | Completed
9734 | APS-G-9375 | APS-G live deployment testing | APS Garland | Navin E,Indumathi,Sangeetha M,Vigneshwaran A,Prabakaran V | Wed 02 Aug 2023 | 36 hrs 6 mins | Completed
9723 | APS-G-9364 | APS-G In Shipping Information , need to be show the countries,states & cities | APS Garland | Sangeetha M | Tue 01 Aug 2023 | 5 hrs 25 mins | Completed
9722 | APS-G-9363 | APS-G Shipping method Analyzing | APS Garland | Sangeetha M | Tue 01 Aug 2023 | 2 hrs 20 mins | Completed
9705 | APS-G-9425 | APS-G Testimonial card desing | APS Garland | Sangeetha M | Tue 01 Aug 2023 | 12 hrs 40 mins | Completed
9565 | APS-G-9206 | APS-G add-on implementation | APS Garland | Sangeetha M | Sat 22 Jul 2023 | 71 hrs 14 mins | Completed
9502 | APS-G-9143 | APS-G Need to change company name in admin login form | APS Garland | Sangeetha M | Tue 18 Jul 2023 | 8 hrs 23 mins | Completed
9500 | APS-G-9141 | APS-G IN shiping Location need to change farmart Logo and Name | APS Garland | Sangeetha M | Sat 15 Jul 2023 | 0 hrs 21 mins | Completed
9499 | APS-G-9140 | APS-G Description in Particular product view need to change | APS Garland | Sangeetha M | Sat 15 Jul 2023 | 0 hrs 42 mins | Completed
9481 | APS-G-9122 | APS GARLAND E-COMMERCE file setup | APS Garland | Navin E,Indumathi,Sangeetha M,Mohamed Ashik,Vigneshwaran A | -- | 36 hrs 42 mins | Completed
9410 | APS-G-9410 | Add testimonials in aps analyzing | APS Garland | Indumathi,Sangeetha M | Tue 11 Jul 2023 | 67 hrs 50 mins | Completed
9326 | -- | APS BOUQUET E-COMMERCE - analyzing | -- | Indumathi,Navin E,Sangeetha M | Thu 06 Jul 2023 | 80 hrs 44 mins | Completed
9313 | EFZ-8954 | Testing & Move to beta in Shredder Entry , Avoid refresh the page while doing actions - completed in local | ERP for ZIGMA | Sangeetha M | Tue 04 Jul 2023 | 3 hrs 13 mins | Completed
9312 | EFZ-8953 | Testing & Move to beta in Shredder Entry , Need to be Entries are only allowed up to the current date | ERP for ZIGMA | Sangeetha M | Tue 04 Jul 2023 | 1 hrs 15 mins | Completed
9299 | EFZ-8940 | Avoid refresh the page while doing actions in Shredder Entry | ERP for ZIGMA | Sangeetha M | Tue 04 Jul 2023 | 5 hrs 7 mins | Completed
9298 | EFZ-8940 | In Shredder Entry , Need to be Entries are only allowed up to the current date | ERP for ZIGMA | Sangeetha M | Tue 04 Jul 2023 | 1 hrs 17 mins | Completed
9293 | EFZ-8934 | Testing & move to Live in Shredder , if Service Hours is reached the particular range , Triggering the mail | ERP for ZIGMA | Sangeetha M | Thu 06 Jul 2023 | 0 hrs | Completed
9292 | EFZ-8933 | Testing & move to Live in Genset Reading , if Service Hours is reached the particular range , Triggering the mail | ERP for ZIGMA | Sangeetha M | Wed 05 Jul 2023 | 1 hrs 11 mins | Completed
9289 | EFZ-8930 | In shredder Entry - Create , Need to be search option in Site Name | ERP for ZIGMA | Sangeetha M | Mon 03 Jul 2023 | 0 hrs 27 mins | Completed
9266 | EFZ-8907 | In Genset Reading & Shredder , if Service Hours is reached the particular range , Triggering the mail | ERP for ZIGMA | Sangeetha M | Sat 01 Jul 2023 | 8 hrs 58 mins | Completed
9253 | EFZ-8894 | Shredder Entry -In close Value , only display the last reading , no need to be based on Entry date | ERP for ZIGMA | Sangeetha M | Fri 30 Jun 2023 | 0 hrs 14 mins | Completed
9245 | EFZ-8894 | Genset Reading Entry - In Sublist , If Already Had Data for Successive Dates, Not Allowed to Delete , Add , Edit records except last record | ERP for ZIGMA | Sangeetha M | Fri 30 Jun 2023 | 0 hrs 33 mins | Completed
9242 | EFZ-8883 | Genset Reading Entry - Testing & Move to Beta | ERP for ZIGMA | Sangeetha M | Fri 30 Jun 2023 | 6 hrs | Completed
9213 | EFZ-8894 | Genset Reading Entry - Approved Time is wrongly displayed in list | ERP for ZIGMA | Sangeetha M | Fri 30 Jun 2023 | 1 hrs 33 mins | Completed
9212 | EFZ-8894 | Genset Reading Entry - Total Hours should be displayed in list & Main Print | ERP for ZIGMA | Sangeetha M | Fri 30 Jun 2023 | 0 hrs 56 mins | Completed
8995 | EFZ-8638 | Internal Zigma Discussion | ERP for ZIGMA | Prabakaran V,Indumathi,mohamed Afrid A,Sangeetha M,Pavithra | Wed 14 Jun 2023 | 11 hrs | Completed
8990 | EFZ-8633 | Upgradation Work - ERP-2111-0127 - For DG, PO should be autogenerated for Oil filter/Fuel filter/Coolant filter and Engine oil if running hours in Shredder Entry form | ERP for ZIGMA | Sangeetha M | Wed 14 Jun 2023 | 51 hrs 20 mins | Completed
8715 | EFZ-8746 | Modified Flow - ERP-2111-0127 - For DG, PO should be autogenerated for Oil filter/Fuel filter/Coolant filter and Engine oil if running hours in Genset Entry form | ERP for ZIGMA | Sangeetha M,Shanmuga Priya K | Wed 31 May 2023 | 109 hrs 6 mins | Completed
8714 | EFZ-8456 | Modified Flow - ERP-2111-0127 - For DG, PO should be autogenerated for Oil filter/Fuel filter/Coolant filter and Engine oil if running hours in Shredder Entry form | ERP for ZIGMA | Manikandan,Sangeetha M | Wed 31 May 2023 | 84 hrs 40 mins | Completed
8427 | EFZ-8075 | DC-entry-> In Delivery Challan need to show GST NO .If vendor had a GST NO | ERP for ZIGMA | Sangeetha M | Mon 15 May 2023 | 1 hrs 53 mins | Completed
8187 | EFZ-7835 | User rights - Multi-site Access - Item Request Approval(List, Print) | ERP for ZIGMA | Sangeetha M | Thu 27 Apr 2023 | 1 hrs 20 mins | Completed
8129 | EFZ-8708 | Zigma portals combination | ERP for ZIGMA | Pavithra,Indumathi,Sangeetha M,Shanmuga Priya K | Thu 27 Apr 2023 | 611 hrs 12 mins | Completed
7848 | EFZ-8264 | ERP-2111-0127 - For DG, PO should be autogenerated for Oil filter/Fuel filter/Coolant filter and Engine oil if running hours in - Genset Reading Entry | ERP for ZIGMA | Sangeetha M | Tue 04 Apr 2023 | 259 hrs 43 mins | Completed
7761 | EFZ-7412 | Sales Order Creation need to change mail "ACTIVE " status based on work order number given by ZIGMA | ERP for ZIGMA | Sangeetha M | Thu 30 Mar 2023 | 2 hrs 8 mins | Completed
7661 | EFZ-7314 | Avoid refresh the page while doing actions in customer_approval form | ERP for ZIGMA | Sangeetha M | Fri 24 Mar 2023 | 11 hrs 39 mins | Completed
7656 | EFZ-7309 | Avoid refresh the page while doing actions in sales order approval form | ERP for ZIGMA | Sangeetha M | Fri 24 Mar 2023 | 7 hrs 47 mins | Completed
7631 | EFZ-7284 | In sales_order_creation ->need to avoid page refresh while mail status ->updating ,adding, editing | ERP for ZIGMA | Sangeetha M | Fri 24 Mar 2023 | 14 hrs 2 mins | Completed
7623 | EFZ-7276 | Need to show old uploaded document in customer creation list page | ERP for ZIGMA | Sangeetha M | Fri 24 Mar 2023 | 5 hrs 54 mins | Completed
7597 | EFZ-7250 | Sales module live updating ->correction work | ERP for ZIGMA | Navin E,Indumathi,Sangeetha M | Fri 24 Mar 2023 | 47 hrs 52 mins | Completed
7596 | EFZ-7331 | Sales order creation ->status need all filter option | ERP for ZIGMA | Sangeetha M | Mon 27 Mar 2023 | 13 hrs 18 mins | Completed
7537 | EFZ-8068 | Tipper entry ->repeated issue analyses and fixing | ERP for ZIGMA | Sangeetha M,Indumathi | Wed 31 May 2023 | 60 hrs 21 mins | Completed
7448 | EFZ-7101 | EHS Moduel ->Baseline Study : need to add sublist for all Analysis Type while create and update | ERP for ZIGMA | Sangeetha M | Tue 14 Mar 2023 | 24 hrs 57 mins | Completed
7385 | EFZ-7182 | Earthmover->report data analyses and fixing issues | ERP for ZIGMA | Manikandan,Indumathi,Sangeetha M | Wed 22 Mar 2023 | 77 hrs 43 mins | Completed
7300 | EFZ-7024 | New workflow for Sales Module | ERP for ZIGMA | Navin E,Sangeetha M,Manikandan | Fri 03 Mar 2023 | 133 hrs 58 mins | Completed
7246 | EFZ-6899 | As per the XLS Sheet attached. Please fill the Remarks From SDPL column alone | ERP for ZIGMA | Praveen S,Navin E,Prabakaran V,Indumathi,Sangeetha M | Tue 28 Feb 2023 | 15 hrs 24 mins | Completed
7225 | EFZ-6878 | Breakdown entry - Newly added fields in Break down entry sublist have to add in both excel export and individual view | ERP for ZIGMA | Sangeetha M | Fri 24 Feb 2023 | 13 hrs 4 mins | Completed
7224 | EFZ-6877 | Breakdown entry - Plant name Filter not working for List, Excel export | ERP for ZIGMA | Sangeetha M | Fri 24 Feb 2023 | 5 hrs 16 mins | Completed
7137 | ZTM-6794 | Import Customer Data of Chattisghar, Bihar, Assam, Arunachal Pradesh, GOA | Zigma - Tender and Marketing Module (ReactJs and Laravel) | Prabakaran V,Sangeetha M | Sat 18 Feb 2023 | 14 hrs 59 mins | Completed
7131 | FC-7131 | Unable to posts - Analysis | Founder Clicks | Sangeetha M | Fri 17 Feb 2023 | 6 hrs 24 mins | Completed
7066 | EFZ-6720 | Overall Excel / Print option required in Shredder entry form. (Excel will be listed the sublist data) | ERP for ZIGMA | Sangeetha M | Wed 15 Feb 2023 | 11 hrs 34 mins | Completed
7065 | EFZ-6719 | Shredder name should be displayed in list (Shredder entry form) | ERP for ZIGMA | Sangeetha M | Wed 15 Feb 2023 | 5 hrs 59 mins | Completed
7064 | EFZ-6718 | Entry person name is not displayed in Shredder entry form | ERP for ZIGMA | Sangeetha M | Tue 14 Feb 2023 | 13 hrs 22 mins | Completed
6845 | EFZ-6501 | User rights - Multi-site Access - all Entry and Report in Operation Module - Live Move | ERP for ZIGMA | Sangeetha M | Sat 11 Feb 2023 | 49 hrs 50 mins | Completed
6834 | EFZ-6490 | Need to avoid atuo fetch google saved password and user name in input filed in Zigma ERP. | ERP for ZIGMA | Sangeetha M | Wed 01 Feb 2023 | 10 hrs 20 mins | Completed
6819 | EFZ-6475 | Zigma New Server -- Initial Testing | ERP for ZIGMA | Praveen S,Sabarieswaran V R,Indumathi,mohamed Afrid A,Manikandan,Sangeetha M,Pavithra,Mahendran Sadasivam,Giri Shankar | Thu 02 Feb 2023 | 61 hrs 1 mins | Completed
6688 | EFZ-6344 | User rights - Multi-site Access - all Entry and Report in Operation Module | ERP for ZIGMA | Sangeetha M | Tue 31 Jan 2023 | 25 hrs 36 mins | Completed
6646 | EFZ-6302 | Machinery Entry - Analysis | ERP for ZIGMA | Sangeetha M | Sat 21 Jan 2023 | 26 hrs 38 mins | Completed
6575 | EFZ-6231 | Live and Local comparision zigma | ERP for ZIGMA | Indumathi,Sangeetha M,Jothi | Wed 18 Jan 2023 | 54 hrs 19 mins | Completed
6548 | EFZ-6204 | Breakdown Entry - Excel - Need to check | ERP for ZIGMA | Sangeetha M | Thu 12 Jan 2023 | 9 hrs 9 mins | Completed
6502 | -- | SVN Local Implementation | -- | Indumathi,Jothi,Sangeetha M | Wed 11 Jan 2023 | 18 hrs 9 mins | Completed
6394 | EFZ-6394 | Sales module - modify existing data for live updating | ERP for ZIGMA | Indumathi,Sangeetha M | Fri 06 Jan 2023 | 9 hrs 38 mins | Completed
6375 | -- | Operation - Add Excel Download Option In Panel Reading & EB Reading & Genset Reading | -- | Sangeetha M | Wed 04 Jan 2023 | 34 hrs 51 mins | Completed
6372 | EFZ-6372 | Operation - In Panel Reading - Add Open & Close reading in Over All Print | ERP for ZIGMA | Sangeetha M | Wed 04 Jan 2023 | 3 hrs 34 mins | Completed
6284 | EFZ-6284 | Sales module updating flow analysis | ERP for ZIGMA | Indumathi,Sangeetha M | Mon 02 Jan 2023 | 54 hrs 42 mins | Completed
6271 | EFZ-6271 | In Sales order creation: customer select option list the customer that particular site will approve by customer approval | ERP for ZIGMA | Sangeetha M | Fri 30 Dec 2022 | 4 hrs 32 mins | Completed
6182 | EFZ-6182 | Zigma - threat code testing | ERP for ZIGMA | Indumathi,Sangeetha M,Jothi | Fri 23 Dec 2022 | 22 hrs 25 mins | Completed
6154 | EFZ-6154 | Security measurement and Testing | ERP for ZIGMA | Sangeetha M | Wed 21 Dec 2022 | 3 hrs 59 mins | Completed
6149 | EFZ-6149 | Security measurement and Testing | ERP for ZIGMA | Sangeetha M | Sat 31 Dec 2022 | 0 hrs 28 mins | Completed
6102 | EFZ-6102 | Confirmation of receipt - print - before image and after image | ERP for ZIGMA | Sangeetha M | -- | 55 hrs 59 mins | Completed
6093 | EFZ-6093 | Customer creation - update not working properly | ERP for ZIGMA | Sangeetha M | Sat 17 Dec 2022 | 4 hrs 10 mins | Completed
6080 | EFZ-6080 | Breakdown report - Total hours is showing wrong | ERP for ZIGMA | Sangeetha M | Fri 16 Dec 2022 | 5 hrs 38 mins | Completed
6030 | EFZ-6030 | SVN server, Client, Xampp, Heidi Installation | ERP for ZIGMA | Sangeetha M | Tue 13 Dec 2022 | 0 hrs 18 mins | Completed
6007 | EFZ-6007 | ERP-2212-0483 - In Jobcard report - in downloaded excel - listed the empty data | ERP for ZIGMA | Sangeetha M | -- | 9 hrs 14 mins | Completed
5993 | EFZ-5993 | NOC Upload - Need to check image and pdf view | ERP for ZIGMA | Sangeetha M | Sat 10 Dec 2022 | 6 hrs 19 mins | Completed
5962 | EFZ-5962 | NOC Upload - Filter not working | ERP for ZIGMA | Sangeetha M | -- | 9 hrs 14 mins | Completed
5945 | EFZ-5945 | SVN Implementation for ZIGMA | ERP for ZIGMA | Sangeetha M | -- | 14 hrs 30 mins | Completed
5854 | EFZ-5854 | ERP-2212-0484 : In jobcard report - Filter not functioning | ERP for ZIGMA | Sangeetha M | Tue 06 Dec 2022 | 6 hrs 48 mins | Completed
5823 | EFZ-5823 | XAMPP and TortoiseSVN Installation | ERP for ZIGMA | Sangeetha M | Mon 05 Dec 2022 | 4 hrs 9 mins | Completed
5627 | -- | PHP with Mysql - Mini Project - Login form, Cateogry Master , Item Master and Sales Form - (Create , List , Update , Delete and Pagination) | -- | Sangeetha M | Thu 24 Nov 2022 | 57 hrs 27 mins | Completed
5611 | -- | Mysql Join - Left join , Right Join, Inner Join and Union | -- | Sangeetha M | Tue 15 Nov 2022 | 0 hrs 57 mins | Completed
5610 | -- | Mysql Insert into Table, Select and Select with Where Conditions (Date , Like , Equal , Not equal , In , Not in and Find in Set) | -- | Sangeetha M | Tue 15 Nov 2022 | 0 hrs 22 mins | Completed
5609 | -- | Mysql Create and Alter Table ( Data types, Primary key and Auto Increament ) | -- | Sangeetha M | Tue 15 Nov 2022 | 2 hrs 50 mins | Completed
5594 | -- | PHP - Mail Sending - Html and Attachment | -- | Sangeetha M | Mon 14 Nov 2022 | 5 hrs 25 mins | Completed
5548 | -- | PHP - ImageSlide | -- | Sangeetha M | Thu 10 Nov 2022 | 20 hrs 12 mins | Completed
5547 | -- | PHP - Checkbox and Selectbox | -- | Sangeetha M | Thu 10 Nov 2022 | 0 hrs 21 mins | Completed
5546 | -- | PHP - Age Calculation with Date Picker | -- | Sangeetha M | Thu 10 Nov 2022 | 1 hrs 45 mins | Completed
5528 | -- | PHP - String Functions - To Upper , To Lower , Index, Split, Find and Replace , Count, Reverse , Explode and Implode | -- | Sangeetha M | Wed 09 Nov 2022 | 10 hrs 23 mins | Completed
5472 | -- | Number to word conversion php | -- | Sangeetha M | Sat 05 Nov 2022 | 24 hrs 13 mins | Completed
5454 | -- | PHP - Find the Ascii Values | -- | Sangeetha M | Fri 04 Nov 2022 | 7 hrs 51 mins | Completed
5434 | -- | Multiplication table using PHP | -- | Sangeetha M | Thu 03 Nov 2022 | 4 hrs 11 mins | Completed
5427 | -- | Image Slider using JavaScript | -- | Sangeetha M | Thu 03 Nov 2022 | 2 hrs 52 mins | Completed
5414 | -- | Javascript - Age Calculation with Date Picker | -- | Sangeetha M | Wed 02 Nov 2022 | 19 hrs 46 mins | Completed